## Sheet1
# | Workflow Step/Task | Sub Steps/ Sub Tasks (if any) | Assumptions | Parallel Task or Dependency | Estimate (Days) | Comments
Handle and PID Django API Application
| Security - Configuring Django to work with HTTPS |  |  | 1: Install SSL certificate to machine. 2: Configure Django to run over Gunicorn. 3: Configure Apache webserver to access django | 4 Days
| Security - Multiple factor authentication for Library staff Django accounts |  |  | 1: Entra account required
| Article model - Django management of article citation metadata |  |  |  | 4 Days
| Provider model - Django management of metadata providers |  |  |  | 4 Days
| Archive model - Django management of archives |  |  |  | 4 Days
| Journal model - Django management of journal caching service |  |  |  | 8 Days
Reports
Design and Documentation
| Overall Design and Architecture for Modernization |  |  |  | 15 Days
| step 1.1 – Move and track archives received through Azure SFTP services |  |  | 1: Access to azure plateform | 4 Days
| step 1.2 - Pull archives from external (S)FTP sites |  |  | 1: Many FTP/SFTP's are not accessible from development machine, hence code to be tested on staging servers | 4 Days
| step 1.3 - NAL's Submission site Harvester |  |  | 1: Many sites are not accessible from development machine, hence code to be tested on staging servers | 5 Days
| step 1.4 - CrossRef Harvester |  |  | 1: API's are not accessible from development machine, hence code to be tested on staging servers | 5 Days
| step 1.5 - CHORUS Harvester |  |  | 1: API's are not accessible from development machine, hence code to be tested on staging servers | 5 Days
| step 2 - Unpack metadata archives and parse to single source records |  |  | 1: Many XML documents have bad formats, and each bad formats needs to handled separately. | 4 Days
| step 3 – Mapping source data to JSON (CrossRef article citation) Standard |  |  |  | 5 Days
| step 4 – Check status of article’s journal in Alma |  |  |  | 7-8 Days
| step-5 – Matching to and merging with existing article in Alma |  |  | Exisiting data is in XML format while we are planning to keep the data in json format. This may take some extra actions and required more testing and debugging. | 12 Days
| step 6 - Metadata quality review |  |  |  | 12 Days
| step 7 – Local metadata enhancement |  |  |  | 12 Days
| step 8 - Annotation with NALT subject terms |  |  |  | 7 Days
| step 9 - Conversion from JSON to MARC XML |  |  |  | 10 Days
| step 10 - Create directory structure for Alma import |  |  |  | 10 Days
| step 11 – Export to Alma Amazon S3 storage |  |  |  | 8 Days
| System Integration Testing |  |  |  | 10 Days
| User Acceptance Testing |  |  |  | 15 Days
| Release to Production |  |  |  | 5 Days