## Modernization - Estimates
# | Workflow Step/Task | Sub Steps/ Sub Tasks (if any) | Assumptions | Parallel Task or Dependency | Estimate (Days) | Comments
| Column1 | Column2 | Column3
Handle and PID Django API Application
Security - Configuring Django to work with HTTPS
Security - Multiple factor authentication for Library staff Django accounts
Article model - Django management of article citation metadata
Provider model - Django management of metadata providers
Archive model - Django management of archives
Journal model - Django management of journal cacheing service
Reports
Design and Documentation
| Overall Design and Architecture for Modernization | 15 Days | Draft
| step 1.1 – Move and track archives received through Azure SFTP services | 4 Days | Draft
| step 1.2 - Pull archives from external (S)FTP sites | 4 Days | Draft
| step 1.3 - NAL's Submission site Harvester | 5 Days | Draft
| step 1.4 - CrossRef Harvester | 5 Days | Draft
| step 1.5 - CHORUS Harvester | 5 Days | Draft
| step 2 - Unpack metadata archives and parse to single source records | 4 Days | Draft
| step 3 – Mapping source data to JSON (CrossRef article citation) Standard | 5 Days | Draft
| Column1 | Column2 | Column3
| step 4 – Check status of article’s journal in Alma | 7-8 Days | Draft
| step-5 – Matching to and merging with existing article in Alma | 7-8 Days | Draft
| step 6 - Metadata quality review | 7-8 Days | Draft
| step 7 – Local metadata enhancement | 7-8 Days | Draft
| step 8 - Annotation with NALT subject terms | 7-8 Days | Draft
| step 9 - Conversion from JSON to MARC XML | 7-8 Days | Draft
| step 10 - Create directory structure for Alma import | 7-8 Days | Draft
| step 11 – Export to Alma Amazon S3 storage | 7-8 Days | Draft
| System Integration Testing | 5 Days | Draft
| User Acceptance Testing | 15 Days | Draft
| Release to Production | 5 Days | Draft

## Documentation - Reference
Wiki page with Cross functional: https://github.com/USDA-REE-ARS/nal_library_system_modernization/wiki Project Charter - https://github.com/USDA-REE-ARS/nal_library_system_modernization/wiki/Project-Charter-%E2%80%90-Article-Citation-Workflow-Modernization Access and Roles: https://github.com/USDA-REE-ARS/nal_django_article_workflow/wiki/Article-workflow-access-roles-and-access